## Ark1
Lofthus frukt og saft
Project start | 2020-02-03
Project end | 2020-03-06 |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 5
Task/activity | Responsible | Time
|  |  | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06
Meeting with customer | Project manager | 1 day
| Copywriter | 1 day
Taking photos | Photographer | 2 days
Editing photos | Photographer | 3 days
Design the website | Graphic designer | 7 days
Create website layout | Front-end developer | 3 days
Create product site | Front-end developer | 3 days
Create shopping basket | Front-end developer | 2 days
Create order form | Front-end developer | 3 days
Create contact sheet | Front-end developer | 1 day
Create live chat | Front-end developer | 1 day
Create FAQ's site | Front-end developer | 1 day
Create photogallery | Front-end developer | 2 days
Test the site | Tester | 2 days
Fix bugs | Front-end developer | 2 days
Show result to customer | Project manager | 1 day
| Front-end developer | 1 day
Fix things customer wants | Front-end developer | 3 days
Deliver product to customer | Project manager | 1 day